INDIAN RAILWAYS AI-POWERED AUTOMATIC BLOCK PLANNING SYSTEM

Comprehensive Mathematical Formulations, Optimization Models & Operational Calculations

Corridor: Prayagraj Junction (PRYJ) - Kanpur Central (CNB) Trunk Route (191 km, 16 Block Sections)
Authors: Aatman Satra (Roll No: C157) & Dishank Shah (Roll No: C181)
Department of Computer Engineering, MPSTME, SVKM's NMIMS, Mumbai (2026-2027)

# 1. Multi-Criteria Decision Analysis (MCDA) Prioritization Engine

Every maintenance demand t in T is evaluated across 5 transparent safety factors on an auditable 100-point scale:

S_t = min(100.0, max(0.0, F_severity + F_overdue + F_density + F_statutory + F_speed + F_mega))

| Factor Name | Symbol | Mathematical Formulation | Points Range |
| --- | --- | --- | --- |
| Safety Severity | F_severity | Emergency = 40.0, Critical = 25.0, Routine = 10.0 | 10.0 - 40.0 pts |
| Overdue Backlog Age | F_overdue | min(20.0, max(0, days_overdue) * 5.0) | 0.0 - 20.0 pts |
| Corridor Traffic Density | F_density | min(15.0, (GMT_section / 150.0) * 15.0) | 8.0 - 15.0 pts |
| Statutory Compliance | F_statutory | 15.0 if is_statutory else 0.0 | 0.0 or 15.0 pts |
| Speed Restriction Relief | F_speed | 10.0 if speed_restriction active else 0.0 | 0.0 or 10.0 pts |
| Executive Mega Block Policy | F_mega | max(10.0, 85.0 - sum(F_baseline)) | 10.0 - 35.0 pts |

Cumulative Block Yield: When tasks t_1, t_2, ..., t_k are co-scheduled into block b:
Yield_b = sum(S_t for t in tasks(b))
Reflects total safety value resolved per unit of corridor possession.

# 2. Google OR-Tools CP-SAT Integer Optimization Formulation

Decision Variables:
- x[t, w] in {0, 1}: Task t scheduled in window w.
- y[w] in {0, 1}: Window w utilized for track possession.
- b[w] in {0, 1}: Window w bundles 2 or more distinct departments.
- d[w, dept] in {0, 1}: Department dept present in window w.

Feasibility Domain:
section_id(t) == section_id(w) AND duration(w) >= min_duration(t)

Hard Constraints:
1. Uniqueness: sum(x[t, w] for w in Feasible) <= 1 for all t in T
2. Activation Linkage: sum(x[t, w] for t in T) >= y[w] AND y[w] >= x[t, w]
3. Bundling Linkage: sum(x[t, w] for t in Dept) >= d[w, dept] AND sum(d[w, dept]) >= 2 * b[w]
4. Intra-Department Sequential Capacity: sum(dur(t) * x[t, w] for t in Dept) <= dur(w)

Multi-Objective Maximization Function:
max sum(W[t, w] * x[t, w]) + sum(10 * beta * b[w]) - sum(lambda * impact[w] * y[w])
- Bundling Bonus: beta = 40 (+400 pts integer bonus)
- Disruption Penalty: lambda = 15 (150 * impact_score penalty)
- Task Weight: W[t, w] = max(10, 10 * S_t - 120 * day_offset + E_emergency + V_speed)
- Emergency Bonus: E_emergency = 1500 * (3 - day_offset) for Day 0 Emergency (+4500 pts)
- Speed Clearance Bonus: V_speed = 300 * (3 - day_offset) for Caution Orders (+900 pts)

# 3. Executive Corridor KPIs & Macro Performance Analytics

1. Bundling Ratio (%): (N_bundled / N_total_blocks) * 100 = (4 / 6) * 100 = 66.7%
2. Asset Availability (%): min(98.5%, 88.0% + (Tasks_Scheduled / Tasks_Demanded) * 10.5%) = 98.5%
3. Idle Downtime Reduction (%): min(85.0%, 45.0% + Bundling_Ratio * 0.4) = 71.7%
4. Backlog Count: max(0, Tasks_Demanded - Tasks_Scheduled) = 13 - 13 = 0
5. Total Block Hours: sum(durations) / 60.0 = 1080 min / 60 = 18.0 hours

# 4. Train Queuing & Delay Propagation Model

1. Avoided Duplicate Closures: N_saved = sum(max(0, len(b.tasks) - 1) for b in Blocks) = 7 Closures
2. Saved Line Shutdown Minutes: T_saved = N_saved * 95 minutes = 665 Minutes
3. Passenger Delay Minutes Saved: D_pax = floor(T_saved * 1.8) = 1,197 Minutes
4. Trains Protected from Loop Regulation: N_trains = round(N_saved * 2.2) = 15 Trains
5. Freight Demurrage Avoided (INR): C_freight = N_saved * 2.4 * 1800 * 1.5 = Rs 45,360 - Rs 1,13,400
6. Corridor Punctuality Index (%): min(99.4%, 84.5% + min(14.0%, 1.8 * N_bundled + 0.015 * T_saved)) = 98.5%
7. Co-Scheduled Efficiency (%): (T_saved / (T_actual + T_saved)) * 100 = (665 / 1745) * 100 = 38.1%

# 5. Interactive What-If Scenario Simulator Formulations

1. Section Density Ratio: R_density = max(0.1, min(1.0, (GMT - 110) / 35))
2. Freight Delay (min): round(max(0, T_proposed - T_thresh) * (0.35 + 0.45 * R_density + 0.15 * Length_flag))
3. Passenger Delay (min): round(max(0, T_proposed - T_pax_thresh) * (0.3 + 0.4 * R_density))
4. Simulated Punctuality (%): max(84.5%, 99.9% - (Freight_Delay * 0.08 + Pax_Delay * 0.35))
5. Safety Score: min(99.6, max(68.0, 72 + (T_proposed / 180) * 18 + OHE_bonus + 5.0 * R_density - Rush_penalty))
6. Demurrage Impact (INR): round((Freight_Delay / 60) * Hourly_Cost)